# ACIDA Project: 1-Year Work Plan

## Overview

This plan delivers the ACIDA (Agri-Climate Information and Digital Advisory) system over 12 months, structured around the proposal's 4 objectives and reconciled with the 6 outputs in the ACIDA Output and Key Activities brief.

Objectives

- Design, develop, and validate the AI-powered ACIDA system

- Establish an integrated geospatial reference database

- Pilot and deploy ACIDA to deliver real-time agri-climate advisories

- Train and strengthen the capacity of farmers and stakeholders to use ACIDA

## Project Timeline

ACIDA 12-month roadmap · 4 quarterly gates

Each quarter closes with a gate: a demoed prototype (Q1), a live platform and database (Q2), a piloted system (Q3), and the final report (Q4).

## Q1 (Months 1–3): Inception & Design

Focus: Objective 1 (design) and the start of Objective 2 (data sourcing).

| Activity/Task | Description | Output |
| --- | --- | --- |
| Project kickoff & partner mapping | Kickoff with project partner NARO and farmer organizations; confirm governance and AEZ selection criteria | Kickoff report; partner engagement plan; list of selected farming areas |
| Farmer needs assessment | Baseline surveys and FGDs with farmers, extension agents, and institutions on information gaps, channel preferences (SMS/USSD/App/WhatsApp), language and literacy needs | Report on farmers' needs and how they prefer to get information (phone call, SMS, app, etc.) |
| System design planning | Finalize the 7-layer ACIDA architecture (access, API, AI/Gen-AI, geospatial, processing, storage, ingestion); select tech stack, hosting, and data governance protocols | Approved technical blueprint showing how ACIDA will be built |
| Identify and secure data sources | Secure soil/crop data from NARO and identify weather, satellite, and market data feeds and SMS/USSD gateway services | List of confirmed data sources (weather, soil, satellite, and market information) |
| Hire the team & purchase equipment | Recruit/assign developers, data scientists, GIS specialists, agronomists; procure IoT sensors, hosting infrastructure, and software licenses | Project team fully hired; first batch of equipment purchased and delivered |
| Build and demonstrate a first working version | Build a minimal working ACIDA prototype covering one full data-to-advisory path: ingest basic weather/geospatial data (sample AEZ boundaries, open weather feeds), generate a simple AI-based advisory, and deliver it via one channel (app or SMS) | A working sample version of ACIDA, ready to demonstrate to stakeholders |

## Q2 (Months 4–6): Platform Development & Geospatial Database Build

Focus: Objective 1 (development) and Objective 2 (database establishment) — scaling the Q1 prototype into the full platform.

| Activity/Task | Description | Output |
| --- | --- | --- |
| Build the system's data-handling engine | Develop the Data Ingestion & Edge layer (IoT/weather station/satellite feeds), Storage & Catalog layer (data lake, metadata catalogue), and Processing & Orchestration layer (ETL, workflow automation) | A working system that can collect, process, and store data, ready for testing |
| Build the climate & farm mapping database | Integrate satellite imagery, soil maps, climate/rainfall data, land-use layers, and crop profiles into a unified database; stand up the mapping engine and raster/tile and vector data services | A working map-based database of weather, soil, and farm information (first version) |
| Build the smart advice engine | Train and calibrate ML models for climate-risk prediction, crop-specific recommendations, and pest/disease alerts; integrate generative AI for advisory text in local languages | First version of the advice engine, tested against past weather and farm records |
| Build the drought alert system (DMEW) | Build drought indicators, monitor rainfall and dry-spell patterns, and develop automated early-warning alert logic integrated into the ACIDA advisory engine | A working drought alert tool that automatically warns farmers of dry spells |
| Build the app, website & messaging channels | Develop the mobile app, web dashboard, and SMS/USSD/WhatsApp integrations; design multilingual and voice interfaces for low-literacy users | Early test versions of the mobile app, website, and SMS/WhatsApp channels |
| Design training materials | Develop training-of-trainers (ToT) curriculum, farmer toolkits, and blended (print + digital) learning materials on using ACIDA and interpreting advisories | Draft trainer's guide and farmer user guides |

## Q3 (Months 7–9): Validation, Pilot Launch & Training Rollout

Focus: Objective 1 (validation), Objective 3 (pilot launch), and Objective 4 (training).

| Activity/Task | Description | Output |
| --- | --- | --- |
| Test that the whole system works correctly | End-to-end testing of all 7 layers (API integration, AI model accuracy, pipeline reliability, UX); fix defects; validate advisory accuracy against agronomist/extension expert review | A fully working, tested version of the ACIDA system |
| Launch the pilot in selected farming areas | Deploy ACIDA in selected pilot sites across representative agroecological zones; onboard pilot farmers and extension agents; begin live data collection | ACIDA up and running in the selected pilot farming areas |
| Train the trainers | Deliver ToT workshops to extension agents and lead farmers using finalized toolkits | A group of certified trainers ready to teach others, with training guides in hand |
| Sign up farmers & partners | Community sensitization, demo sessions, and digital literacy support to register farmers on app/SMS/WhatsApp channels | Pilot farmers signed up and starting to receive advice; list of registered users |
| Start sending live advice to farmers | Commence delivery of seasonal forecasts, DMEW early-warning alerts, and risk-management advisories across all channels; begin collecting usage/feedback data | First round of weather and farming advice delivered to pilot farmers |

## Q4 (Months 10–12): Scale-Up, M&E & Final Reporting

Focus: Objective 3 (continued piloting), Objective 4 (capacity strengthening), and project-wide M&E/closeout.

| Activity/Task | Description | Output |
| --- | --- | --- |
| Keep sending advice & improve the system | Sustain real-time advisory delivery across pilot sites; use farmer feedback and usage analytics to refine AI models, UX, and content relevance | An improved version of ACIDA that gives more accurate advice and is easier to use |
| Expand training to more farmers & partners | Extend training to additional farmer groups and other actors; broaden toolkit distribution and blended learning sessions | More farmers and organizations trained and confident using the system; training guides shared widely |
| Track results & measure impact | Track adoption/uptake, advisory accuracy, farmer satisfaction, and early resilience/productivity indicators; conduct endline survey against the Q1 baseline | Final evaluation report showing how well the project worked |
| Write up lessons learned & share with government | Document lessons learned and case studies; share findings and sustainability pathways with NARO and government stakeholders | Case studies and a short summary for policymakers, shared with government and partners at a public event |
| Write the final report & plan for the future | Compile the final project report covering all 4 objectives/outputs; develop a financing, ownership, and maintenance plan for post-project sustainability | Final project report and a plan for keeping the system running after the project ends |

## Expected Outputs by Quarter

| Output | Description | Delivered In |
| --- | --- | --- |
| Agri-climate digital database developed | Integrated geospatial reference agri-climate database (weather, climate, soil, and agricultural data) | Built Q2, operational from Q3 |
| Farm-specific Agri-Climate Advisory Tool developed | Fully functional and validated ACIDA agri-climate decision-support system | Prototype delivered Q1; built out Q2; validated Q3; refined Q4 |
| Drought Monitoring and Early Warning (DMEW) system developed | DMEW module generating drought indicators and early-warning alerts, integrated into the ACIDA advisory engine | Developed Q2, live from Q3 |
| Prototype tested and validated | ACIDA prototype piloted on selected farms, user feedback collected, and the system refined | Built Q1; piloted and validated Q3; refined with feedback Q4 |
| Farmers and stakeholders trained | Structured capacity-building training programs and ACIDA toolkits for farmers and extension workers | Designed Q2, delivered Q3 (ToT), scaled Q4 |
| Project results disseminated | Technical reports, lessons learned, system demonstrations, and findings shared with stakeholders | Compiled and shared Q4 |

## Change Log - Plain-Language Simplification (2026-10-22)

On 2026-10-22, the Activity/Task and Output columns across the Q1-Q4 tables were rewritten in plain language for non-technical stakeholders. The table below records every technical term or phrase that was changed and its simplified replacement. Description columns and the Expected Outputs by Quarter summary table (which mirrors the ACIDA Output and Key Activities brief) were not altered.

| Quarter | Field | Original (Technical) | Plain-Language Version |
| --- | --- | --- | --- |
| Q1 | Task | Project inception & stakeholder mapping | Project kickoff & partner mapping |
| Q1 | Output | Inception report; stakeholder engagement plan; list of selected agroecological zones | Kickoff report; partner engagement plan; list of selected farming areas |
| Q1 | Task | Needs assessment & user requirements | Farmer needs assessment |
| Q1 | Output | Baseline/needs assessment report with user personas and channel preferences | Report on farmers' needs and how they prefer to get information (phone call, SMS, app, etc.) |
| Q1 | Task | System architecture & technical design | System design planning |
| Q1 | Output | Approved system architecture and technical design document | Approved technical blueprint showing how ACIDA will be built |
| Q1 | Task | Data source identification & access | Identify and secure data sources |
| Q1 | Output | Data inventory register | List of confirmed data sources (weather, soil, satellite, and market information) |
| Q1 | Task | Team mobilization & procurement | Hire the team & purchase equipment |
| Q1 | Output | Full project team in place; procurement plan with initial equipment delivered | Project team fully hired; first batch of equipment purchased and delivered |
| Q1 | Task | Rapid prototype build & demo | Build and demonstrate a first working version |
| Q1 | Output | Working ACIDA prototype (MVP) | A working sample version of ACIDA, ready to demonstrate to stakeholders |
| Q2 | Task | Build core data pipeline | Build the system's data-handling engine |
| Q2 | Output | Functional ingestion-to-storage data pipeline running in staging | A working system that can collect, process, and store data, ready for testing |
| Q2 | Task | Build the geospatial reference database | Build the climate & farm mapping database |
| Q2 | Output | Operational geospatial reference agri-climate database (v1) | A working map-based database of weather, soil, and farm information (first version) |
| Q2 | Task | Develop AI/ML & Gen-AI advisory models | Build the smart advice engine |
| Q2 | Output | First-version advisory models validated against historical data (offline testing) | First version of the advice engine, tested against past weather and farm records |
| Q2 | Task | Develop Drought Monitoring & Early Warning (DMEW) module | Build the drought alert system (DMEW) |
| Q2 | Output | Operational DMEW module generating early-warning alerts | A working drought alert tool that automatically warns farmers of dry spells |
| Q2 | Task | Build user access & delivery channels | Build the app, website & messaging channels |
| Q2 | Output | Beta mobile app, web dashboard, and messaging channels ready for internal testing | Early test versions of the mobile app, website, and SMS/WhatsApp channels |
| Q2 | Task | Design capacity-building curriculum & toolkits | Design training materials |
| Q2 | Output | Draft ToT curriculum and ACIDA user toolkits | Draft trainer's guide and farmer user guides |
| Q3 | Task | System integration testing & validation | Test that the whole system works correctly |
| Q3 | Output | Fully functional, validated ACIDA system (v1) | A fully working, tested version of the ACIDA system |
| Q3 | Task | Pilot deployment in AEZs | Launch the pilot in selected farming areas |
| Q3 | Output | ACIDA live and operational in pilot AEZs | ACIDA up and running in the selected pilot farming areas |
| Q3 | Task | Training-of-Trainers (ToT) | Train the trainers |
| Q3 | Output | Cohort of certified trainers equipped with toolkits | A group of certified trainers ready to teach others, with training guides in hand |
| Q3 | Task | Farmer & stakeholder onboarding | Sign up farmers & partners |
| Q3 | Output | Pilot farmers registered and receiving advisories; onboarding database | Pilot farmers signed up and starting to receive advice; list of registered users |
| Q3 | Task | Real-time advisory delivery begins | Start sending live advice to farmers |
| Q3 | Output | First cycle of real-time agri-climate advisories delivered to pilot farmers | First round of weather and farming advice delivered to pilot farmers |
| Q4 | Task | Continuous advisory delivery & platform refinement | Keep sending advice & improve the system |
| Q4 | Output | Refined ACIDA platform (v2) with improved advisory accuracy and user satisfaction | An improved version of ACIDA that gives more accurate advice and is easier to use |
| Q4 | Task | Scale-up capacity-building & institutional training | Expand training to more farmers & partners |
| Q4 | Output | Strengthened farmer and institutional capacity; toolkits rolled out at scale | More farmers and organizations trained and confident using the system; training guides shared widely |
| Q4 | Task | Monitoring, evaluation & impact assessment | Track results & measure impact |
| Q4 | Output | M&E/endline report with key outcome indicators | Final evaluation report showing how well the project worked |
| Q4 | Task | Documentation, knowledge products & policy engagement | Write up lessons learned & share with government |
| Q4 | Output | Knowledge products (case studies, policy brief) and a stakeholder dissemination event | Case studies and a short summary for policymakers, shared with government and partners at a public event |
| Q4 | Task | Final reporting & sustainability planning | Write the final report & plan for the future |
| Q4 | Output | Final project report and sustainability/scale-up plan | Final project report and a plan for keeping the system running after the project ends |